## Signed contracts (3-j)
Reconstruction of the 4R105 "Darband-Boysun-Elbayon"on the section 5-70 km and 4R100 "Manguzor-Dzharkurgan-Bandikhon-Altynsai-Denau" on the section 128-174 km with the participation of the Asian Development Bank (ADB)
No. | Total packages/lots in the project | Contract value (in US dollars) | Name of Organization/Consultant | Contract signing date | Contract expiry date | Execution of contracts
[6 empty] | 2022 |  |  |  |  | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
[6 empty] | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June
| General | 161266578
1 | Civil works, including: |  |  |  |  | 2027 June: 30 June 2027: Loan closing date under Loan Agreement 4174-UZB
1.1 | Lot 1: Reconstruction of the 4R105 "Darband-Boysun-Elbayon" on the section 5-37,5 km | 49300707.14 | Open Joint Stock Company "Lankaran Yol Tikinti" (Azerbaijan) | 2023-10-06 | 2027-02-11 | 2023 February: 2023-02-12; 2023 March: Construction and installation works; 2025 February: 2025-02-11; 2025 March: Defects Notification Period; 2027 February: 2027-02-11
1.2 | Lot 2: Reconstruction of 4R105 “Derband-Boysun-Elbayon” on the section 37,5-70 km | 28551505.97 |  |  | 2027-04-14 | 2023 April: 2023-04-15; 2023 May: Construction and installation works; 2025 April: 2025-04-14; 2025 May: Defects Notification Period; 2027 April: 2027-04-14
1.3 | Lot 3: Reconstruction of the 4R100 “Manguzor-Zharkurgan-Bandikhon-Altynsai-Denau” on section 128-174 km | 69742028.09 |  |  | 2027-05-18 | 2023 May: 2023-05-19; 2023 June: Construction and installation works; 2025 May: 2025-05-18; 2025 June: Defects Notification Period; 2027 May: 2027-05-18
1.4 | Construction of 52,9 km rural roads in Surkhandarya region | 8683667.3 |  | 2024-03-01 | 2027-03-01 | 2024 March: 2024-03-01; 2024 April: Construction and installation works; 2025 March: 2025-03-01; 2025 April: Defects Notification Period; 2027 March: 2027-03-01
2 | Construction Supervision Consultant | 4595549.5 | Dongsung Engineering Co., Ltd. and Meinhardt Pte. LLC joint venture (Korea-Singapore) | 2023-10-24 | 2027-05-22 | 2022 November: 2023-11-22; 2027 May: 2027-05-22
3 | National Environmental Specialist | 51000 | Jurabekov Shodiyor | 2022-07-08 | 2025-12-31 | 2022 September: 2022-09-08; 2025 December: 2025-12-31
4 | National Resettlement Specialist | 14500 | Olimov Furqat | 2024-12-13 | 2025-12-31 | 2025 January: 2025-01-06; 2025 December: 2025-12-31
5 | National External Monitoring Specialist | 8000 | Royka Ekaterina | 2022-08-30 | 2026-11-30 | 2022 September: 2022-09-19; 2026 November: 2026-11-30
6 | National Gender Expert | 43980 | Mirzaeva Shakhnoza | 2023-04-11 | 2027-04-11 | 2023 April: 2023-04-11; 2027 April: 2027-04-11
7 | Consulting services for External Financial Audit | 31020 | LLC "TSIAR-FINANCE" | 2023-05-03 | 2026-07-03 | 2023 May: 2023-05-12; 2026 July: 2026-07-12
8 | Consulting services for Internal Audit | 44620 | PKF MAK ALLIANCE LLC | 2023-05-22 | 2025-11-22 | 2023 May: 2023-05-24; 2025 November: 2025-11-24
9 | International Concrete Pavement Specialist | 100000 | Ramesh Chand Vishwakarma | 2023-05-15 | 2026-06-04 | 2023 June: 2023-06-05; 2026 June: 2026-06-04
10 | International Contract Management Specialist | 100000 | Shambhu KS | 2023-07-27 | 2026-08-13 | 2023 August: 2023-08-14; 2026 August: 2026-08-13